## ICB (hidden)
STW ICB Exit Criteria Metrics
Exit Criteria | Focus Area |  | Metric | Proposed Metrics?? | Progress Inc Milestones / Tracjectories | Output(s) | Impact | Required Evidence?
1 | Finance | Develop and deliver a single Recovery Plan (“the Recovery Plan”), to be agreed with NHS England, that brings together the ICB, provider and additional system wide recovery initiatives, that has clear demonstrable improvement in financial performance for 2024/25 including supporting metrics such as increased efficiency delivery (cost reduction), adherence to agency rules and workforce numbers. This is to have Board agreement from all STW organisations and is signed off Regionally and Nationally. And have an agreed Capital Plan that is clearly aligned to system strategic priorities, supporting the financial recovery plan with realistically agreed funding sources. | 1.1 | The system has an agreed medium term financial plan in place that has been signed off by the Board and agreed with the ICS and NHS England's Regional team. |  | Development of a system financial anlysis linked to 2024/25 operational plan , that clearly maps and agreed "do nothing" underlying financial position and projection |  | This analysis to be supported by detailed workforce and activity planning
Using GIRFT Model Hospital and other external metrics develop a financial recovery plan
All component parts of the system are to have a plan that is consitent with other system partners.
Sustainable financial balance to be achieved by [ 31 March 2028]
[6 empty] | All plans to include the impact of the new hospital and associated revenue costs |  | Finance projections to be to at least 12 months after full opening of the new hospital
All efficiency plans for the first 36 months of the plan to be identified and supported by a clear PID and implementation programe
All other efficincy programmes reconciled to "opportuniteis" identified by external benchmarking and with evidenced support form all oranisations in the system and professional bodies.
Robust workforce and activity plan which is aligned to the MTFP so as to demonstrate how workforce efficiencies implicit in financial plans will be delivered in practice, with triangulation to safer staffing guidelines and agreed clinical activity plans
|  |  | 1.2 | The organisation can demonstrate sustainable delivery of its financial and workforce plans |  | Achievement of all plans and trajectories for at least 6 months after agreement to include at least one year end
Completion of all required public consultation porcess required linked to any service reconfiguration inherent in the financial recovery plan
Completion of all staff side cosultations and / or orgaisational reconfigurations required as part of the recovery plan.
|  |  | 1.3 | Robust financial controls and processes are in place and overseen through appropriate financial governance procedures |  | All organisations achieve "substantile" assurance from Head of Internal Audit |  | No outstanding internal audit actions are outstnading of more than 12 months.
In the 6 months prior to the regional recommendation for exit an self assessment against "grip and control checklist" , and oter best praactice guidance,including detailed review of processess and effectiveness of workforce controls (recruitment and bank / agency use)
Independent reivew of self assessment to include agreement with conclusions in checklist and accuracy of sell-assessment itself
Review of Finance Sub-Committee to ensure effectiveness and any other governanc eprocess deemed appropriate.
2 | Workforce | Develop and deliver a plan that is signed off Regionally and Nationally, that has Board agreement from all STW organisations and is signed off Regionally and Nationally, that is clearly aligned to system strategic priorities and financially sustainable
3 | U&EC | Develop and deliver a comprehensive, system-wide Urgent and Emergency Care Improvement plan (“the Improvement Plan”) which demonstrates the appropriate system actions and controls in place for improving U&EC access, quality and performance across the whole U&EC pathway, including an outline of how the ICB demonstrates it has robust escalation procedures in place (both in and out of hours) for addressing system capacity, utilisation and the management of risk.
4 | Governance | Implement sufficient programme management and governance arrangements across system providers to enable delivery and reporting of improvement, with immediate focus being on Finance and U&EC.
5 | Leadership | Demonstrate collaborative decision-making at both system and organisational levels, based on the principle of delivering the best, most sustainable and most equitable solutions for the whole population served by the system

## STW Finance Summary
STW System Transition Criteria - Finance |  |  | CEO Lead Simon Whitehouse, Exec Lead Claire Skidmore, Programme Lead Angela Szabo
DETAIL: What you need to deliver against to exit the Recovery Support Programme (RSP) and transition from NOF4 to NOF3 | Metric ID | System Deliverable Owner | KEY DELIVERABLES: The outputs that you need to produce to demonstrate delivery of exit criteria | METRICS: The measure you will track to understand if the deliverables are delivering the right results | MILESTONES / TRAJECTORY: What needs to be achieved and by when to transition from NOF4 to NOF3 by March 2026 | EVIDENCE Where the metrics are currently reported (or where could we get this data from) and/or any specific deliverables required as evidence of delivery
Develop and deliver a single Recovery Plan (“the Recovery Plan”), to be agreed with NHS England, that brings together the ICB, provider and additional system wide recovery initiatives, that has clear demonstrable improvement in financial performance for 2024/25 including supporting metrics such as increased efficiency delivery (cost reduction), adherence to agency rules and workforce numbers. This is to have Board agreement from all STW organisations and is signed off Regionally and Nationally. Have an agreed Capital Plan that is clearly aligned to system strategic priorities, supporting the financial recovery plan with realistically agreed funding sources. | 1.1 | Angela Szabo | The system has an agreed medium term 3-5 year financial plan (MTFP) in place that has been signed off by the Board and agreed with the ICS and NHS England (capital and revenue) Triangulation exercise - financial plan to workforce, activity and performance plans; with evidence of testing and review against the HTP model. To be included with the MTFP for sign off. A further +5 year high level summary plan is required to align with HTP timescales and underlying financial balance for the system. MTFP to include a summary of efficiencies linked to benchmarking opportunities | Plans are set out in the deliverables - signed off plans are the measure of success. Delivery of overall planned position (ie to reach breakeven) - N/A as anticipated to be post RSP exit | Annual refresh of MTFP and +5 year high-level financial plan (including triangulation) by 31st March each year (internal system deadline 31st December). | Signed off 3-5 year MTFP Signed off +5 year high-level financial plan Financial Strategy Governance: individual finance committees and Boards; System Finance Committee and Board. Evidence of full sign off through meetings with NHSE regional and national teams.
| 1.2 | Angela Szabo Plans Ian Bett CIPs/PIDs | 24/25 and 25/26 financial plans (revenue) agreed and signed off by all component organisations and NHS England Plans to include a fully developed Financial Improvement Plan (i.e. CIPs) with supporting PIDs linked to the benchmarking opportunities | Development of Plan 24/25 plan already signed off by all parties and in progress 25/26 plan - sign off by all parties will be the measure of success Delivery of Plan ICS financial performance plan vs actual ICB financial performance plan vs actual CIP plan vs actual Comparison of prior year (3 years) efficiency delivery to 24/25 plan (absolute figure; % of income; % recurrent) with a breakdown of the 'anatomy' of the savings - ie non recurrent measures; procurement savings; transformation. This is to demonstrate sufficient ambition in the 24/25 plan | Material delivery of the 24/25 agreed financial plan and subsequent 25/26 plan across the system as a whole. Fully developed Financial Improvement Plan with supporting PIDs for 24/25 by end of Sept 24 and majority of 25/26 by end of March 25. Overall 24/25 efficiency delivery demonstrates clear cost reduction that is greater than in previous years and has a strong recurrent element when benchmarked against other Systems. | Monthly finance reports (to individual organisations and system finance committees and boards) Benchmark delivery vs peers (% variance to plan for the financial position and recurrent savings as a % of overall efficiency programme) Financial Improvement Plan with supporting PIDs for 24/25 and 25/26
| 1.3 | Angela Szabo | Capital plans for 24/25 and 25/26 signed off by all component organisations and NHS England | ICS financial capital performance plan vs actual ICB financial capital performance plan vs actual Capital Delegated Expenditure Limit (CDEL) | End of year 24/25 End of year 25/26 Not to exceed CDEL | Monthly finance reports (to individual organisations and system finance committees and boards) Financial Strategy (includes capital)
| 1.4 | Angela Szabo | Independent review of 'grip & control' - identifying gaps (I&I phase 1 work) resulting in a plan to address the gaps Follow up re-assessment review of 'grip & control' | Agreed subset of controls from the 'grip & control' checklist, plus associated impact measurement - linked to the identified gaps Wider review of all controls in the 'grip & control' checklist at the follow up re-assessment review | Quarter on quarter delivery of the impact metrics related to gaps Maintain performance in areas that scored well at initial external review Follow-up review in August 2025 | Data on metrics related to gaps produced monthly Results of the Follow up re-assessment review of 'grip & control' demonstrating required improvements Internal Audit findings for all finance related audits to be rated moderate or substantial External Audit Opinion, VFM

## STW Finance Plan
Metric ID | Deliverable(s) The outputs that you need to produce to demonstrate delivery of exit criteria | Deliverable Owner | Task ID | Task(s) The tasks you need to complete to produce the deliverables (please add / remove lines as necessary) | Task Owner | Start Date | End Date
1.1 | The system has an agreed medium term 3-5 year financial plan (MTFP) in place that has been signed off by the Board and agreed with the ICS and NHS England (capital and revenue) Triangulation exercise - financial plan to workforce, activity and performance plans; with evidence of testing and review against the HTP model. To be included with the MTFP for sign off. A further +5 year high level summary plan is required to align with HTP timescales and underlying financial balance for the system. | Angela Szabo | STW 1.1.1 | System and ICB MTFP planning assumptions agreed and base case model developed and shared with system finance committee (Complete) | Andy Chandler | 2024-07-01 | 2024-09-26
|  |  | STW 1.1.2 | System and ICB MTFP planning assumptions agreed and base case model developed and shared with individual finance committees (Complete) | Andy Chandler | 2024-07-01 | 2024-09-26
|  |  | STW 1.1.3 | System and ICB Recovery trajectories over 2,3,4, and 5 years and high-level financial impact modelled (Complete) | Andy Chandler | 2024-08-02 | 2024-08-13
|  |  | STW 1.1.4 | System and ICB Operational performance, clinical and quality impact aligned to recovery trajectories over 2,3,4, and 5 years | Angela Szabo | 2024-11-01 | 2024-12-31
|  |  | STW 1.1.5 | System Finance strategy first draft developed and shared with System Finance Committee (Complete) | Angela Szabo | 2024-07-01 | 2024-09-26
|  |  | STW 1.1.6 | Review System JFP Finance in line with updated strategy document | Angela Szabo | 2024-10-18 | 2024-10-25
|  |  | STW 1.1.7 | System Demand and capacity 1 year model developed (Complete) | Craig Kynaston | 2024-07-01 | 2024-09-30
|  |  | STW 1.1.8 | System Demand and capacity 3-5 years model developed | Craig Kynaston | 2024-10-01 | 2024-12-31
|  |  | STW 1.1.9 | System Demand and capacity 1-5 year model updated for 25/26 planning assumptions and agreed MTFP planning assumptions | Craig Kynaston | 2025-01-01 | 2025-02-28
|  |  | STW 1.1.10 | System and ICB MTFP triangulation to activity, workforce and performance and updated for 25/26 operational planning guidance. | Andy Chandler | 2024-12-01 | 2025-02-28
|  |  | STW 1.1.11 | System/ICB Application of the Strategic Decision Making Framework to prioritise business cases for investment, financial improvement programme and strategic transformation programmes. | Gemma Smith/Angela Szabo | 2024-10-01 | 2025-03-31
|  |  | STW 1.1.12 | Recovery plan trajectory based Strategic Transformation Programmes including HTP, LCP and Benchmarking opportunities, updated in Finance Strategy and MTFP model. | Angela Szabo | 2024-10-01 | 2025-01-31
|  |  | STW 1.1.13 | Approval of recovery trajectory updated MTFP and Finance Strategy through individual organisational boards | Angela Szabo | 2025-02-01 | 2025-02-28
|  |  | STW 1.1.14 | Approval of recovery trajectory updated MTFP and Finance Strategy through system finance committee and ICB board | Angela Szabo | 2025-02-01 | 2025-03-31
|  |  | STW 1.1.15 | Recovery plan trajectory agreed with all individual organisations, system and NHSE. | Angela Szabo | 2025-01-01 | 2025-03-31
|  |  | STW 1.1.16 | Ongoing monitoring of the delivery of plans and potential changes to the MTFP logged each quarter | Andy Chandler | 2024-07-01 | 2026-03-31
|  |  | STW 1.1.17 | MTFP annual refresh completed | Andy Chandler | 2024-07-01 | 2025-03-31
|  |  | STW 1.1.18 | 10 year capital plan developed (Complete) | Angela Szabo | 2024-07-01 | 2024-07-31
|  |  | STW 1.1.19 | Update 10 year capital plan following the release of 25/26 guidance. | Angela Szabo | 2024-12-01 | 2025-01-31
|  |  | STW 1.1.20 | Apply the Capital Prioritisation Framework to arrive at an agreed list of system and ICB prioritised capital projects matched to available capital resource taking into account the impact of non-investment. | Angela Szabo | 2024-12-01 | 2025-01-31
|  |  | STW 1.1.21 | Approval of System and ICB Capital 10 year plan through individual organisational boards | Angela Szabo | 2025-02-01 | 2025-02-28
|  |  | STW 1.1.22 | Approval of System Capital 10 year plan through system finance committee and infrastructure strategy through strategic commissioning committee | Angela Szabo | 2025-02-01 | 2025-03-31
|  |  | STW 1.1.23 | Approval of System Capital 10 year plan and infrastructure strategy through ICB Board and NHSE | Angela Szabo | 2025-01-01 | 2025-03-31
|  |  | STW 1.1.24 | Develop System and ICB long term financial plan model to include planning assumptions agreed in the MTFP and the full impact of HTP and other Strategic Transformation Programmes - capital and revenue. | Andy Chandler | 2025-01-01 | 2025-01-31
|  |  | STW 1.1.25 | Recovery plan trajectory based Strategic Transformation Programmes including HTP, LCP and Benchmarking opportunities, updated in the LTFP model. | Andy Chandler | 2025-02-01 | 2025-02-28
|  |  | STW 1.1.26 | System High level 10 year LTFP signed off by all individual organisations, system and NHSE. | Angela Szabo | 2025-03-01 | 2025-03-31
|  |  | STW 1.1.27 | MTFP annual refresh completed | Andy Chandler | 2026-01-01 | 2026-03-31
1.2 | 24/25 and 25/26 financial plans (revenue) agreed and signed off by all component organisations and NHS England Plans to include a fully developed Financial Improvement Plan (i.e. CIPs) with supporting PIDs linked to the benchmarking opportunities | Angela Szabo Plans Ian Bett CIPs/PIDs | STW 1.2.1 | 2024/25 System and ICB Revenue financial plan agreed and submitted to NHSE following approval through individual organisational and system governance and NHSE (Complete) | Angela Szabo | 2024-01-01 | 2024-06-12
|  |  | STW 1.2.2 | System and ICB 24/25 CIP plan fully identified and PIDs in place for all schemes. (Complete).​ | Ian Bett | 2024-01-01 | 2024-09-30
|  |  | STW 1.2.3 | Individual organisational financial control processes enhanced for workforce and via system workforce meeting (vacancy panel - substantive, bank and agency).​ | Angela Szabo PWC supporting via individual organisations | 2024-04-01 | 2024-12-31
|  |  | STW 1.2.4 | De-risk high risk CIP schemes, generate mitigations and accelerate pipeline schemes. ​ | Angela Szabo PWC supporting via individual organisations | 2024-04-01 | 2024-12-31
|  |  | STW 1.2.5 | Identify risk mitigations via Financial Recovery Groups in individual organisations.​ NHSE Opportunities List Unpalatable Decisions | Angela Szabo PWC supporting via individual organisations | 2024-10-01 | 2024-11-20
|  |  | STW 1.2.6 | Financial plan delivery - monthly monitoring via finance committee (risks and mitigations, efficiency delivery and run-rate) - includes oversight of Financial Improvement Programme | Angela Szabo | 2024-04-01 | 2025-03-31
|  |  | STW 1.2.7 | Complete Phase 2 I&I workforce, UEC and system PMO deliverables.​ | Angela Szabo PWC supporting via individual organisations | 2024-09-01 | 2024-12-31
|  |  | STW 1.2.8 | Identify and agree system transformation programmes to unpin recovery plan.​ | Angela Szabo PWC supporting via individual organisations | 2024-10-01 | 2024-12-31
|  |  | STW 1.2.9 | 25/26 CIP targets agreed with individual organisations with increased recurrent delivery of CIP.​ | Angela Szabo PWC supporting via individual organisations | 2024-10-01 | 2025-03-31
|  |  | STW 1.2.10 | 25/26 CIP plan (or multi-year CIP plan) agreed with individual organisations to address key drivers of excess cost and benchmarking opportunities.​ | Angela Szabo PWC supporting via individual organisations | 2024-10-01 | 2025-03-31
|  |  | STW 1.2.11 | Full Year Effect of 24/25 CIPs to be confirmed.​ | Kate Owen | 2024-10-01 | 2024-03-31
|  |  | STW 1.2.12 | Development of pipeline schemes for 25/26 to address (where agreed) excess cost drivers, model health system opportunities, NHSE efficiencies list opportunities, productivity, workforce and UEC, HTP, other strategic programmes and benchmarking opportunities. | Kate Owen | 2024-10-01 | 2024-12-31
|  |  | STW 1.2.13 | 25/26 CIP plan fully identified and majority of PIDs completed in line with new system PMO governance and signed off through individual oragnisational governance SWG/FRG and system governance FIP | Kate Owen | 2024-10-01 | 2025-03-31
|  |  | STW 1.2.14 | Update 25/26 financial planning assumptions for 25/26 operational guidance and commissioning intentions. | Andy Chandler | 2024-11-01 | 2024-12-31
|  |  | STW 1.2.15 | Productivity improvement plan and productivity efficiencies developed for 25/26 | Andy Chandler | 2024-11-01 | 2025-03-31
|  |  | STW 1.2.16 | Undertake confirm and challenge process for System and ICB 25/26 cost pressures | Angela Szabo | 2024-11-01 | 2025-01-31
|  |  | STW 1.2.17 | Application of the Strategic Decision Making Framework to prioritise System and ICB business cases for investment. | Gemma Smith/Angela Szabo | 2024-10-01 | 2025-02-28
|  |  | STW 1.2.18 | Update 25/26 financial plan to take account of efficiency plans, investment decisions and other operational planning decisions | Andy Chandler | 2024-12-01 | 2025-03-31
|  |  | STW 1.2.19 | 25/26 financial plan triangulation to activity, workforce and performance. | Andy Chandler | 2024-12-01 | 2025-02-28
|  |  | STW 1.2.20 | Approval of 25/26 financial plan through individual organisational boards, system finance committee and NHSE | Angela Szabo | 2025-02-01 | 2025-03-31
1.3 | Capital plans for 24/25 and 25/26 signed off by all component organisations and NHS England | Angela Szabo | STW 1.3.1 | 24/25 Capital Plan agreed June 24 System Finance Committee, agreed by all STW organisations and NHSE (Complete). | Angela Szabo | 2024-01-01 | 2024-06-12
|  |  | STW 1.3.2 | System Delivery of 24/25 CDEL - application of the Capital prioritisation framework in action in year. Performance monitoring through CPOG - Capital report Prioritisation Oversight Group, application of the Capital Prioritisation Framework as required. (Monthly). | Angela Szabo | 2024-04-01 | 2025-03-31
|  |  | STW 1.3.3 | System Capital Strategy & Capital Prioritisation Framework developed with system partners and approved at System Finance Committee June 2024. (Complete).​ | Angela Szabo | 2024-05-01 | 2024-06-30
|  |  | STW 1.3.4 | Draft System Infrastructure strategy developed and submitted to NHSE July 24 for review (Completed)​ | Angela Szabo | 2024-01-01 | 2024-07-31
|  |  | STW 1.3.5 | Initial system capital plan 25/26 populated in July 24 (Complete). | Angela Szabo | 2024-05-01 | 2024-07-31
|  |  | STW 1.3.6 | System and ICB Capital prioritisation within available resource for 25/26 once funding limits following guidance is confirmed. | Angela Szabo | 2024-11-01 | 2025-03-31
|  |  | STW 1.3.7 | Update Infrastructure Strategy following NHSE feedback - approval at SCC Feb 25 and Board March 25 | Angela Szabo | 2024-11-01 | 2025-03-31
|  |  | STW 1.3.8 | Update the 25/26 Capital plan following the release of national capital guidance and sign-off by individual organisation and system governance and NHSE. | Angela Szabo | 2024-11-01 | 2025-03-31
|  |  | STW 1.3.9 | Delivery of 25/26 CDEL - application of the Capital prioritisation framework in action in year. Performance monitoring through CPOG - Capital report Prioritisation Oversight Group, application of the Capital Prioritisation Framework as required. (Monthly). | Angela Szabo | 2025-04-01 | 2026-03-31
1.4 | Independent review of 'grip & control' - identifying gaps (I&I phase 1 work) resulting in a plan to address the gaps Follow up re-assessment review of 'grip & control' | Angela Szabo | STW 1.4.1 | Phase 1 I&I - External review assessment of Individual organisational self-assessment of NHSE grip and control checklist & HFMA Financial Sustainability checklist. (Complete). | Angela Szabo | 2024-07-01 | 2024-08-15
|  |  | STW 1.4.2 | Delivery against Phase 1 I&I organisation specific intervention action plans (No PO No Pay, efficacy of vacancy and temporary staffing controls and de-risking cost efficiency schemes - system PMO actions captured on Governance). Key outputs reported in finance report to finance committee monthly. | Angela Szabo | 2024-08-15 | 2024-11-30
|  |  | STW 1.4.3 | Delivery of Phase 2 I&I scope in relation to efficacy of controls (run-rate improvements) for Workforce, UEC and System PMO (high risk CIPs)​ - delivery of interventions post PWC Phase 2 completion by March 25. | Ian Bett with PWC supporting | 2024-09-15 | 2025-03-31
|  |  | STW 1.4.4 | External review of Individual organisation assessment against NHSE grip and control checklist & HFMA Financial Sustainability checklist and efficacy of controls. | Angela Szabo | 2025-07-01 | 2025-08-15
|  |  | STW 1.4.5 | Delivery of individual organisational internal audit report recommendations from prior years and pro-active management in year (Monthly review). | Angela Szabo | 2024-04-01 | 2026-03-31
|  |  | STW 1.4.6 | Individual organisational tracking of timely completion of internal audit actions (Monthly). | Angela Szabo | 2024-04-01 | 2026-03-31
|  |  | STW 1.4.7 | Delivery of individual organisational external audit report recommendations to include aligned individual and system MTFP (Monthly review). | Angela Szabo | 2024-04-01 | 2026-03-31
|  |  | STW 1.4.8 | Individual organisational tracking of timely completion of external audit actions (Monthly). | Angela Szabo | 2024-04-01 | 2026-03-31
|  |  | STW 1.4.9 | Internal Audit findings for all finance related audits to be rated moderate or substantial | Angela Szabo | 2024-04-01 | 2026-03-31
|  |  | STW 1.4.10 | External audit and HOIAO audits including VFM to be rated moderate or substantial | Angela Szabo | 2024-04-01 | 2026-03-31

## STW Finance Risks Mitigations
[8 empty] | Initial Rating |  |  |  |  | Target risk score
SIIP Risk ID | Strategic Pledge/ Purpose | Date opened | Risk title and description | Opportunity | Existing key controls | Existing source of assurance | Gaps in controls / assurances | C | L | Score | Risk Score Trend | Mitigating Actions | C2 | L2 | Score2 | Director or risk owner | Risk Owner | Committee / Board Oversight | Amendments name and date
STWFIN 1 | 1,2,3 | 2024-08-01 | Data Warehousing Data Reporting, Data Quality Issue - Elective data reported below planned levels due to Data Quality issues. Risk to System ERF Income delivery. | Opportunity to create a financially sustainable system | Monthly Contract Review Meetings Weekly SaTH/ICB operational meetings Monthly data reporting meeting | Fortnightly System Delivery Meetings Monthly Finance Committee Meetings | Gaps in controls: None Gaps in assurances: None | 4 | 5 | 20 |  | Weekly operational meeting in place across SaTH/ICB - focused action plan based on identified issues, with weekly cycle of issue resolution, tests and sign off by BI and Finance. Expert additional resource brought in to deliver plan with oversight by NHSE, interim solution identified. Longer term solution also under development. Adding staff capacity to increase capacity and activity. National payment variation requested to allow implementation of interim solution, additional capacity to accelerate (NHSE scoping). | 4 | 3 | 12 | Claire Skimore, CFO | Angela Szabo, DOF | ICB and System Finance Committees | Matched to latest SORR (note this as per Risk reported to November FC)
STWFIN 2 | 1,2,3 | 2023-08-01 | Risk to delivery of the Financial Improvement Programme - Resource constraints to support the full identification and delivery of the 2024/25 Financial Improvement Programme and development of the multi-year FIP programme | Opportunity to create a financially sustainable system | Regular (weekly) organisational Provider Financial Recovery Group and Monthly ICB Sustainability Working Group to assess capacity and deliverability of deadlines | Monthly financial reporting to finance committee at both an ICB and ICS level Staff capacity reviewed at finance team meetings and regularly reviewed with ICS CFO. System Finance, Training and Development Council in place to develop and support a strengthened finance community Organisational review of capacity at Provider Financial Recovery Group (weekly) and ICB Sustainability Working Group (Monthly) | Gaps in controls: 1. Finance and PMO capacity is extremely limited. System reporting and delivery requirements dealt with through existing organisational finance teams. Gaps in assurances: None | 3 | 4 | 12 |  | Financial improvement plans are now fully identified for 24/25, PIDs developed and required mitigations identified against the initial plans. Phase 1 I&I complete, Phase 2 I&I supporting delivery in UEC, Workforce and System PMO alongside additional PMO support agreed for CHC. Further system mitigations and unpalatable decisions under discussion. | 3 | 3 | 9 | Claire Skimore, CFO | Angela Szabo, DOF | ICB and System Finance Committees | Matched to latest SORR (note this as per Risk reported to November FC)
STWFIN 3 | 1,2,3 | 2024-04-22 | Risk to the delivery of the 2024/25 Financial Plan - 2024/25 Financial Risks are : Efficiency Delivery Risk £19.8m Month 6(100% High Risk plus 25% of Medium risk, reduced from £28.5m Month 5) Cost Risk £39m Month 6 (Reduced from £59.4m in Month 5 - HCA re-banding risk increased) Income Risk £29.7m Month 6 (Reduced from £30.4m Month 5) | Opportunity to create a financially sustainable system | Revenue and Capital System financial principles and risk management framework in place across the system as part of development of system financial recovery plan approach as set out within the financial strategy. System governance arrangements in place through finance committee and system strategic committee and commissioning working group to ensure that new investments are not made unless recurrent resource is available. Revenue System workforce programme and agency reduction group implemented, weekly agency reporting and action plan to reduce agency expenditure in line with system cap Financial Improvement Programme and System Transformation Group Organisation self assessments of plan conditions/financial controls in place - Triple Lock, vacancy controls, HFMA sustainability and NHSE Grip and Control. System vacancy panel in place. Workforce monitoring of vacancies in place. Capital Capital Prioritisation Oversight Group | Regular System level financial reporting to ICS finance committee and Integrated Care Board Finance Committee across the system to oversee efficiency and transformation programme delivery. System productivity and FIP group in place for efficiency. FIP reports into System Transformation Group which provides Assurance to the Board Provider collaborative in place. System agency reduction group implemented, weekly agency reporting and action plan to reduce agency expenditure in line with system cap. NOF organisation self assessments of plan conditions/financial controls, Triple lock in place. | Gaps in Control: STW 12th June Revenue Financial Plan Limit £90m deficit, Efficiency is 7.14% for the ICS - Fully identified efficiency plans for 24/25 now in place. Key areas of risk to delivery are: 1.a Efficiency delivery risk 1b Escalation costs due to UEC pressure and links to discharge 1c Costs and inflation pressures 1d New NICE appraisals with significant implementation costs e.g. Obesity - Tirzepatide could have huge financial impacts (circa £81M if 70% eligible patients were able to access at current list price) 1e Income Risk if NHSE Income assumptions in the forecast are not supported e.g. Spec Comm ERF for RJAH, Endoscopy income at SaTH Gaps in Assurances: A forecast that does not have risks fully mitigated means that there is limited assurance that the financial forecast can be met. | 4 | 5 | 20 |  | Efficiency - System PMO and FIP Governance in place to address £14.9m high risk schemes, including weekly action plans to de-risk delivery with oversight from Executive leads supported by PWC through the Phase 2 I&I. Cost - Workforce Controls/Non-Pay Controls in place and System Governance for reporting and oversight . Income - NHSE decisions awaited on spec comm ERF RJAH, SaTH Endoscopy and junior doctors funding and national payment variation requested in relation to SaTH Data Reporting issue. | 4 | 3 | 12 | Claire Skimore, CFO | Angela Szabo, DOF | ICB and System Finance Committees | Matched to latest SORR (note this as per Risk reported to November FC)

## STW Workforce Summary
STW System Transition Criteria - Workforce |  |  | CEO Lead Stacey Keegan, Exec Lead Rhia Boyode, Programme Lead Simon Balderstone
DETAIL: What you need to deliver against to exit the Recovery Support Programme (RSP) and transition from NOF4 to NOF3 | Metric ID | System Deliverable Owner | KEY DELIVERABLES: The outputs that you need to produce to demonstrate delivery of exit criteria | METRICS: The measure you will track to understand if the deliverables are delivering the right results | MILESTONES / TRAJECTORY: What needs to be achieved and by when to transition from NOF4 to NOF3 by March 2026 | EVIDENCE Where the metrics are currently reported (or where could we get this data from) and/or any specific deliverables required as evidence of delivery
Develop and deliver a workforce improvement plan, that has Board agreement from all STW organisations and is signed off Regionally and Nationally, that is clearly aligned to system strategic priorities and financially sustainable | 2.1 | Simon Balderstone | Workforce delivery plans for 24/25 and 25/26 signed off by all component organisations and NHS England | Delivery against workforce plan including required reduction in agency | Material delivery of the 24/25 agreed workforce plan and subsequent 25/26 plan across the system as a whole. | Board & NHS England signed off workforce delivery plans Monthly workforce actual vs plan reports Benchmark delivery vs peers
| 2.2 | Rhia Boyode | Refreshed People and OD strategy | Reduction in staff unplanned absence, unavailability (baseline 23/24) Improvement in retention (baseline 23/24) Reduction in funded establishment vacancy levels (baseline 23/24) Staff survey results (baseline 23/24) Staff turnover out of area as % (baseline 23/24) | Sustained improvement quarter on quarter for staff unplanned absence & retention Improved pulse results in 24/25 & 25/26 & NHS staff survey results in 24/25 and completion rate in 25/26. | Board approved People & OD Strategy including recruitment and retention strategy Monthly workforce reports actual vs plan for absence and retention Annual staff survey results Benchmark delivery vs peers

## STW Workforce Plan
Metric ID | Deliverable(s) The outputs that you need to produce to demonstrate delivery of exit criteria | Deliverable Owner | Task ID | Task(s) The tasks you need to complete to produce the deliverables (please add / remove lines as necessary) | Task Owner | Start Date | End Date
2.1 | Workforce delivery plans for 24/25 and 25/26 signed off by all component organisations and NHS England | Simon Balderstone | STW 2.1.1 | Identify baseline and outturn forecast | Planning leads | 2024-11-04 | 2024-11-30
|  |  | STW 2.1.2 | Review known changes, service changes needed, and business cases approved from 24/25 | Planning leads | 2024-12-02 | 2024-12-31
|  |  | STW 2.1.3 | Outline any assumptions in terms of workforce metrics, turnover absence levels etc | Planning leads | 2024-12-02 | 2024-12-31
|  |  | STW 2.1.4 | Populate Workforce Planning Template | Richard W | 2025-01-06 | 2025-01-31
|  |  | STW 2.1.5 | Calculate the % Change by Staff Group | Richard W | 2025-01-06 | 2025-01-31
|  |  | STW 2.1.6 | Challenge / Sense Check Data | Richard W | 2025-02-03 | 2025-02-28
|  |  | STW 2.1.7 | Review Data with Stakeholders | Jan H / Simon B | 2025-02-03 | 2025-02-28
|  |  | STW 2.1.8 | Populate Master Template and Triangulate with Finance and Operations | Jan H / Simon B | 2025-02-03 | 2025-02-28
|  |  | STW 2.1.9 | Final Sign Off - Board and NHSE | Rhia B | 2025-03-03 | 2025-03-31
|  |  | STW 2.1.10 | Set up and deliver workshop with People and OD team and Divisional reps to identify the priority areas needed that support delivery of our workforce plan | Jan H / Simon B | 2024-11-04 | 2024-11-30
|  |  | STW 2.1.11 | Develop set of actions and milestones that support each priority area with time frame and actions owners | Jan H / Simon B | 2024-12-02 | 2024-12-31
|  |  | STW 2.1.12 | Finalise plan with fully supported narrative describing the impact and benefit of delivery the plan | Jan H / Simon B | 2024-12-02 | 2024-12-31
|  |  | STW 2.1.13 | Capture risks to delivery of plan and any mitigations to reduce risk | Jan H / Simon B | 2024-12-02 | 2024-12-31
|  |  | STW 2.1.14 | Develop summary project plan showing high level timescale – Gantt chart | Jan H / Simon B | 2024-12-02 | 2024-12-31
|  |  | STW 2.1.15 | Gain sign off from each provider and NHS England | Rhia B | 2025-01-06 | 2025-01-31
|  |  | STW 2.1.16 | Ensure actions and milestones monitoring is incorporated into fortnightly agenda of workforce planning and assurance group and Agency reduction group. Ongoing monitoring | Simon B | 2025-01-06 | 2026-03-31
2.2 | Refreshed People and OD strategy | Rhia Boyode | STW 2.2.1 | Set up planning workshop (1st workshop) with key stakeholders (people leaders across the system) to identify key drivers of workforce challenges and risks | Alison T | 2024-12-02 | 2024-12-31
|  |  | STW 2.2.2 | Review data and workforce metrics helping to provide insights into future risks and challenges | Jan H / Simon B | 2024-12-02 | 2024-12-31
|  |  | STW 2.2.3 | Engage with wider stakeholders, such as patient groups, unions and staff networks to determine views on priorities set up survey (if required) | Rhia B | 2025-01-06 | 2025-01-31
|  |  | STW 2.2.4 | Capture risk and strategic priorities | Alison T | 2025-01-06 | 2025-01-31
|  |  | STW 2.2.5 | Hold 2nd workshop with stakeholders to set out a long-term People and OD vision fit for the future | Alison T | 2025-02-03 | 2025-02-28
|  |  | STW 2.2.6 | Major engagement across events with the public and staff, online platforms and face to face sessions | Alison T | 2025-02-03 | 2025-02-28
|  |  | STW 2.2.7 | Capture suggested actions, milestones and benefits to support strategic priorities | Alison T / Simon B | 2025-02-03 | 2025-02-28
|  |  | STW 2.2.8 | Agree and finalise set of actions / priorities | Alison T / Simon B | 2025-03-03 | 2025-03-31
|  |  | STW 2.2.9 | Develop final document for review | Alison T / Simon B | 2025-03-03 | 2025-03-31
|  |  | STW 2.2.10 | Gain feedback from system partners and make any necessary adjustments to strategy | Rhia B | 2025-03-03 | 2025-03-31
|  |  | STW 2.2.11 | Commission graphic design to produce final document | Alison T / Simon B | 2025-03-03 | 2025-04-30
|  |  | STW 2.2.12 | Take through People Collaborative and gain approval and sign off | Rhia B | 2025-03-03 | 2025-04-30
|  |  | STW 2.2.13 | Monitor delivery of stratgey via key metrics to ensure strategy is delivered and working effectively | Rhia B | 2026-04-30 | 2026-03-31

## STW Workforce Risks Mitigations
[8 empty] | Initial Rating |  |  |  |  | Target risk score
SIIP Risk ID | Strategic Pledge/ Purpose | Date opened | Risk title and description | Opportunity | Existing key controls | Existing source of assurance | Gaps in controls / assurances | C | L | Score | Risk Score Trend | Mitigating Actions | C2 | L2 | Score2 | Director or risk owner | Risk Owner | Committee / Board Oversight | Amendments name and date
STWWORK1 | ICS Aim: Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning | 22.10.24 | Reduced workforce planning capacity and expertise impacts ability to develop plan for 25/26. | Greater collaborative working across workforce teams to share skills and knowledge facilitated by joint roles across SaTH and SCHT. NHSE funding for CIPD Strategic Workforce Planning course. | Additional bank support . Additional technical support available. | System Workforce Group. Planning Deputies Group. STW People Collaborative Committee. System Planning & Performance Group. | N/A | 3 | 4 | 12 |  | Review of people team structure underway, will develop proposed structure – looking to share resources across SaTH / SCHT / ICB, which will help but more resource to support workforce planning is required. Action: Seek support from NHSE for workforce planning resource across system. | 3 | 3 | 9 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK2 | ICS Aim: Tackling Inequalities in Outcomes, Experience and Access; Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning | 22.10.24 | Continued reliance on agency temporary workforce, adversely impacting quality. Performance and financial plans | Agency reduction programme including regional initiative. | Improved governance controls in place, low vacancy levels due to previous years international recruitment campaigns | Weekly workforce returns to NHSE. System Workforce Group. System Vacancy Panel. | N/A | 3 | 3 | 9 |  | System agency taskforce group set up along with NHSE Price Cap Compliance programme which will focus on price and reducing volume. Actions •Write to all agencies and advice of the work underway to pay out price cap by end of March 25 for all nursing specialities. • Set up data set and reporting – to benchmark across region • Set plan to gradual reduce rates from now to March – earlier if possible | 3 | 2 | 6 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK3 | ICS Aim: Tackling Inequalities in Outcomes, Experience and Access; Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning | 22.10.24 | The level of workforce unavailability (absences via sickness, parental leave etc) remain high impacting need for temporary workforce or creating unfilled gaps across services | Review of unavailability factors to develop improvement plan. | Monitoring absence levels via system vacancy dashboard | System Workforce Group. System Financial Improvement Group. | N/A | 4 | 3 | 12 |  | Introduced programme to support all aspects of unavailability management (including, strengthened absence management policy, improved rostering etc) Actions: Review unavailability mitigation being undertaken at SaTH and assess relevance and applicability at SCHT by December 24 | 3 | 3 | 9 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK4 | ICS Aim: Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning and Retain - Looking After Our People | 22.10.24 | Turnover / workforce leavers rates increase creating higher demand for recruitment than planned | CSU resource to support Retain programme. | Monitoring absence levels via system vacancy dashboard | System Workforce Group. System Vacancy Panel. STW People Collaborative Committee. | N/A | 3 | 3 | 9 |  | Retention programme in place across system with focus on flexibility, health and wellbeing and leadership | 3 | 2 | 6 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK5 | ICS Aim: Enhancing Productivity & Value for Money People Strategy: Retain - Looking After Our People; Train - Growing for the Future | 22.10.24 | Levels of staff engagement decrease as a result of cultural and leadership challenges across the system impacting levels of workforce productivity | Refresh of People & OD Strategy provides opportunity to re-engage and re-energise workforce | Leadership and cultural programmes running | STW People Collaborative Committee | N/A | 3 | 3 | 9 |  | Provider response to staff survey in place including action plans centred around leadership and cultural improvement Action: Contact other systems and providers based on recommendations from NHSE to support with best practice on improving culture and staff engagement by December 24. | 3 | 2 | 6 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK6+A9:R12 | ICS Aim: Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning | 2024-10-01 | Reduction of WTE not achieved in full in 2024/25 taking into account the impact on WTE of additional £6m stretch | PWC support to identify additional WTE reduction schemes | Workforce Efficiency Schemes | System Workforce Group. System Vacancy Panel. STW People Collaborative Committee. | N/A | 4 | 4 | 16 |  | Process implemented at System Vacancy Panel to track dis-established posts. All roles reviewed are compared to plan and minimum staffing levels at service level. Establishment reviews underway, refined vacancy panel criteria via Phase 2 I&I. Alternative schemes developed. | 3 | 3 | 9 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK7 | ICS Aim: Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning | 2024-10-01 | Pay pressures for bank and agency staff. | System MoU in principle to harmonise agency & bank rate cards. Regional initiative to harmonise agency rates. | Workforce Efficiency Schemes | System Workforce Group. System Financial Improvement Group. STW People Collaborative Committee. | N/A | 4 | 4 | 16 |  | System approach to negotiation on rates with agency providers – also to be progressedat regional level . Roll out of NHSP bank across system. Improved e-rostering. Focus on price cap overrides. WM Cluster medical rates. Strengthening of approval processes for bank shifts. Increased focus on workforce unavailability. Enhanced bank rates ceased. | 4 | 3 | 12 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK8 | ICS Aim: Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning | 2024-10-01 | Increased escalation costs. | Local Care transformation programme, HTP, primary care improvement programme. | UEC improvement programme. Virtual Wards, RRU. | UEC Board. System Workforce Group. System Financial Improvement Group. STW People Collaborative Committee. | N/A | 4 | 4 | 16 |  | Escalation plan is reviewed and challenged at UEC Board and FIP. I&I PwC Phase 2 support, focused on driving improvement and impact. | 4 | 3 | 12 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24
STWWORK9 | ICS Aim: Enhancing Productivity & Value for Money People Strategy: Reform - New Ways of Working & Strategic Workforce Planning | 2024-10-01 | Impact of cessation of RJAH LLP contracton finance, activity and waiting lists. | Increased reliance on substantive and bank staff. Reduced agency expenditure. | RJAH plan for contract expiry. | System Workforce Group. Financial Improvement Group. Finance Deputies Group. System Planning & Performance Group. STW People Collaborative Committee. | N/A | 4 | 4 | 16 |  | Mitigation plan in place inc. alternative staffing through NHS locum appointments, and HTE framework, SLAs with other local trusts, review job plans and rostering practices to optimise substantive staffing | 3 | 3 | 9 | Rhia Boyode | Workforce SRO | People Collaborative Committee | J Heath 20/11/24

## STW UEC Summary
STW System Transition Criteria - UEC |  |  | CEO Lead Jo Wlliams, Exec Lead Ian Bett, Programme Lead Gareth Wright
DETAIL: What you need to deliver against to exit the Recovery Support Programme (RSP) and transition from NOF4 to NOF3 | Metric ID | System Deliverable Owner | KEY DELIVERABLES: The outputs that you need to produce to demonstrate delivery of exit criteria | METRICS: The measure you will track to understand if the deliverables are delivering the right results | MILESTONES / TRAJECTORY: What needs to be achieved and by when to transition from NOF4 to NOF3 by March 2026 | EVIDENCE Where the metrics are currently reported (or where could we get this data from) and/or any specific deliverables required as evidence of delivery
Develop and deliver a comprehensive, system-wide Urgent and Emergency Care Improvement plan (“the Improvement Plan”) which demonstrates the appropriate system actions and controls in place for improving U&EC access, quality and performance across the whole U&EC pathway, including an outline of how the ICB demonstrates it has robust escalation procedures in place (both in and out of hours) for addressing system capacity, utilisation and the management of risk. | 3.1 | Gareth Wright | System UEC Improvement Plans 24/25 and 25/26 25/26 plan to be finalised when national guidance for 25/26 is published | Plans for 24/25 and 25/26 | 25/26 Planning to be linked HY1 evaluation commencing 02/09/2024 | Board approved system wide UEC Improvement Plan (including PIDs)
| 3.1.1 | Sara Biffen | Workstream 1: 4hr performance | 4 hr performance Ambulance handover performance Patients >12hrs | 78% by March 25 (Type 1 &3) Reduce ambulance handover dealys >3hrs to no more than 4.5 per day by March 2025 12 hours reduce to no more than 17.2% (of Type1 attendances) by March 2025 | UEC Dashboard, UEC Delivery Group reports
| 3.1.2 | Lawrence Ginder | Workstream 2: Accident & Emergency Medicine, Medical and Internal Professional Standards | Patients>12hrs >14 and >21 day LoS ALoS (acute) Escalation beds reduced in line with plan | 12 hours as above +21 day patients 76 by end of March 2025 +14 day patients 151 by end of March 2025 ALoS (currently only have simple ) 4.1 March 2025 Escalation spaces 0 end of March 2025 | UEC Dashboard, UEC Delivery Group reports
| 3.1.3 | Claire Horsfield | Workstream 3: Alternatives to ED and Care coordination | Reduction in level of avoidable ED attendances and admissions Plan v Actual | Current working hypothesis prior to ED ecist front door day that took place 12th August WCS- -2.7% decrease on plan March 2025 RCS- -3% decrease on plan March 2025 BCS- -4.4% decrease on plan March 2025 | UEC Dashboard, UEC Delivery Group reports Refreshed Optimity data - quaterly showig reduction in sometimes and usually avoidable targetted cohorts
| 3.1.4 | Vanessa Whateley | Workstream 4: System Frailty (to be lead by the ICB) | LoS in fraility unit Reduction in waiting time in ED for >65yrs Contribute to reduction in non admitted patients >12hrs | FAU measures in SaTH frailty dashboard Delirium and Falls pathway counted in the ATED numbers | UEC Dashboard, UEC Delivery Group reports
| 3.1.5 | Michael Bennett | Workstream 5: System Discharge | Level of NCTR (acute & community) Average LoS NCTR (acute & community) Escalation capacity reduced in line with plan | NCTR in SaTH 94 March 2025 NCTR to discharge LoS 2 days March 2025 Escalation spaces 0 end of March 2025 Community metrics levelof 20 NCTR, ALoS NCTR of 4 days by March 25. | UEC Dashboard, UEC Delivery Group reports
| 3.2 | Gareth Wright | Effective governance and oversight of the delivery of the plan | Minimum of 10 UEC Delivery Group per year Attendance at UEC DeliveryGroup by partner UEC risk register and ongoing reduction in overall risk score. | Delivery of metrics to the right for 24/25 and 25/26 | UEC Delivery Group attendance list UEC System Risk Register

## STW UEC Plan
Metric ID | Deliverable(s) The outputs that you need to produce to demonstrate delivery of exit criteria | Deliverable Owner | Task ID | Task(s) The tasks you need to complete to produce the deliverables (please add / remove lines as necessary) | Task Owner | Start Date | End Date
3.1 | System UEC Improvement Plans 24/25 and 25/26 25/26 plan to be finalised when national guidance for 25/26 is published | Gareth Wright | STW 3.1.0.1 | Implement the Winter & H2 Priorities guidance 16 Sep 24 | Ian Bett | 2024-09-16 | 2024-11-30
|  |  | STW 3.1.0.2 | UEC Plan 24/25 6 month review supported by PwC | Gareth Wright | 2024-09-25 | 2024-10-21
|  |  | STW 3.1.0.3 | 6 month review to UEC Delivery Group (UEC DG) Oct meeting | Ian Bett | 2024-10-22 | 2024-10-22
|  |  | STW 3.1.0.4 | Develop additional winter mitigations following UEC DG | Ian Bett | 2024-10-23 | 2024-11-11
|  |  | STW 3.1.0.5 | Design next round of UEC Improvement for H1 25/26 | Gareth Wright | 2024-11-01 | 2024-11-30
|  |  | STW 3.1.0.6 | Align H1 24/25 Improvement to ICB Planning round | Gareth Wright | 2024-12-01 | 2024-12-31
|  |  | STW 3.1.0.7 | System UEC Improvement Plan 25/26 development | Gareth Wright | 2024-11-01 | 2024-12-31
|  |  | STW 3.1.0.8 | Finalise System UEC Improvement Plan 25/26 | Ian Bett | 2024-01-01 | 2025-01-31
|  |  | STW 3.1.0.9 | Triangulate Improvement Plan 25/26 with Quality & Finance | Gareth Wright | 2025-02-01 | 2025-02-28
|  |  | STW 3.1.0.10 | Operationalise the Improvement Plan 25/26 | Ian Bett | 2025-03-01 | 2026-03-31
3.1.1 | Workstream 1: 4hr performance | Ned Hobbs | STW 3.1.1.1 | Review and recommission UTC provision to increase utilisation | Rebecca Houlston | 2024-10-01 | 2025-04-01
|  |  | STW 3.1.1.2 | Implement admission avoidance clinics to reduce demand on ED | Gordon Wood | 2024-04-01 | 2024-11-30
|  |  | STW 3.1.1.3 | Implement further GP direct access speciality pathways across Womens and Childrens services | Zain Siddiqui | 2024-05-12 | 2025-04-01
|  |  | STW 3.1.1.4 | Implement GP direct access speciality pathways across surgical services | Andrena Weston | 2024-05-12 | 2025-04-01
|  |  | STW 3.1.1.5 | Improve productivity of Minors | Rebecca Race/Rebecca Houlston/Nat Rose/Deb Archer | 2024-05-13 | 2025-01-01
|  |  | STW 3.1.1.6 | Review ED Medical staffing to ensure it aligns with the hourly demand with both ED departments | Rebecca Race | 2024-05-31 | 2024-12-31
3.1.2 | Workstream 2: Accident & Emergency Medicine, Medical and Internal Professional Standards | Laurence Ginder | STW 3.1.2.1 | Improve response time to referrals on the AMU & Medical wards (currently 24 hours) by Cardio and Respiratory | Saskia Jones-Perrott | 2024-05-21 | 2025-04-30
|  |  | STW 3.1.2.2 | Review effectiveness of the Admission and Referral Protocol following relaunch | Steve McKew | 2024-05-24 | 2025-04-30
|  |  | STW 3.1.2.3 | Reconfiguration of bed base on PRH site to expand acute medical beds to align with demand | Laura Graham | 2024-11-01 | 2025-07-01
|  |  | STW 3.1.2.4 | Recruitment following reconfiguration of Cardiorespiratory to optimise diagnostics | Tom Phelps | 2024-05-31 | 2025-03-31
|  |  | STW 3.1.2.5 | Therapies - Review the use of SPA time and the SOP updating if required | Emma Weaver | 2024-07-01 | 2024-11-30
|  |  | STW 3.1.2.6 | Therapies - Review the impact of the E-job planning trial and agree next steps | Emma Weaver | 2024-07-01 | 2024-11-30
|  |  | STW 3.1.2.7 | Therapies - Review Stroke Pathways considering the opportunities as outlined in the CQC report | Emma Weaver | 2024-07-01 | 2024-12-31
|  |  | STW 3.1.2.8 | Radiology - Gap analysis against proposed 12hr turnaround | Helen Williams | 2024-10-01 | 2024-10-31
|  |  | STW 3.1.2.9 | Radiology - 12hr turnaround draft proposal including procedures and SOP | Helen Williams | 2024-10-01 | 2024-11-30
|  |  | STW 3.1.2.10 | Pharmacy - Development of business case for Pharmacy staff in ED | Imran Hanif | 2024-10-28 | 2024-11-30
|  |  | STW 3.1.2.11 | Pharmacy - Procurement / Installation / Staff Training / Go live of automated cabinets at PRH emergency dept. | Imran Hanif | 2024-10-21 | 2025-03-31
|  |  | STW 3.1.2.12 | Pathology - Recruitment of additional posts to extend out of hours provision | Adrian Verdee | 2024-11-01 | 2025-03-31
3.1.3 | Workstream 3: Alternatives to ED and Care coordination | Claire Horsfield | STW 3.1.3.1 | Review and update DoS to ensure correct utilisation as available alternatives to ED | Sam Townsend | 2024-02-22 | 2024-09-30
|  |  | STW 3.1.3.2 | Develop service provision out of hours for community services (VW, RR, DNs) to further support admission avoidance | Claire Horsfield | 2024-05-08 | 2024-09-02
|  |  | STW 3.1.3.3 | Review current gaps against A-tED specification | Claire Horsfield | 2024-06-17 | 2024-05-10
|  |  | STW 3.1.3.4 | Care co-ordination evaluation via GiRFT & ECIST | Claire Horsfield | 2024-05-06 | 2024-09-30
3.1.4 | Workstream 4: System Frailty (to be lead by the ICB) | Vanessa Whatley | STW 3.1.4.1 | Establish Frailty Assessment Units at RSH & PRH | Alison Massey & Angela Raynor | 2024-05-20 | 2025-03-01
|  |  | STW 3.1.4.2 | Frailty Clinical advice & guidance line as part of the FAU offer | Angela Raynor | 2024-05-20 | 2025-03-01
|  |  | STW 3.1.4.3 | Introduce a System wide delirium pathway | Alison Massey & Angela Raynor | 2024-05-20 | 2025-03-01
|  |  | STW 3.1.4.4 | Adoption of Rockwood as system-wide Clinical Frailty Scale and increased use of SPICT | Alison Massey | 2024-05-23 | 2025-03-01
|  |  | STW 3.1.4.5 | Develop plan for improvement of UTI prevention and catheter care emergency attendances | Alison Massey | 2024-05-23 | 2025-03-01
|  |  | STW 3.1.4.6 | Implementation of comprehensive geriatric assessment in care homes | Alison Massey | 2024-05-01 | 2024-12-06
|  |  | STW 3.1.4.7 | Integrated Falls Prevention and Urgent Falls Response Programmes | Alison Massey | 2024-07-01 | 2024-08-31
|  |  | STW 3.1.4.8 | Energize, Fit4All and Community Champions programme of work | Alison Massey | 2024-07-01 | 2024-08-31
|  |  | STW 3.1.4.9 | Process developments of Long Lie & Urgent Falls pathways | Alison Massey | 2024-07-01 | 2024-08-31
|  |  | STW 3.1.4.10 | Roll out of the managing deterioration pathway (National Patient safety Programme) | Alison Massey | 2024-10-19 | 2025-02-01
|  |  | STW 3.1.4.11 | Frailty intervention team extended hours | Alison Massey | 2024-12-06 | 2025-02-01
3.1.5 | Workstream 5: System Discharge | Michael Bennett | STW 3.1.5.1 | Reduce length of stay for NCTR patients by process improvements in the System Discharge Alliance, with earlier identification of complex patients on wards prior to discharge | Mark O'Brien | 2024-04-01 | 2025-03-31
|  |  | STW 3.1.5.2 | Develop and establish a System Care Transfer Hub [Fully operational from 1 Oct 24 and incrementally delivering the required effects] | Michael Bennett | 2024-08-19 | 2024-09-30
|  |  | STW 3.1.5.3 | Improve the pathway profile to promote Home First [Connected to the CTH implementation] | Michael Bennett | 2024-08-19 | 2024-09-30
3.2 | Effective governance and oversight of the delivery of the plan | Gareth Wright | STW 3.2.1 | Reset UEC Programme after ICB leadership change | Ian Bett | 2024-09-01 | 2024-09-30
|  |  | STW 3.2.2 | Reset UEC Delivery Group after SaTH leadership change | Jo Wheeler | 2024-09-15 | 2024-09-30
|  |  | STW 3.2.3 | Reactivate UEC Clinical Advisory Group led by ICB CMO | Lorna Clarson | 2024-10-01 | 2024-11-30
|  |  | STW 3.2.4 | Tighten UEC DG outputs to System Transformation Group | Gareth Wright | 2024-10-22 | 2024-10-31
|  |  | STW 3.2.5 | Clarify governance UEC DG to SaTH UEC TAC, LCTP, Quality | Gareth Wright | 2024-10-23 | 2024-11-26
|  |  | STW 3.2.6 | UEC DG 6 month review of Plan 24/25 | Gareth Wright | 2024-10-22 | 2024-10-22
|  |  | STW 3.2.7 | UEC DG framing of System UEC Improvement Plan 25/26 | Gareth Wright | 2024-11-26 | 2024-11-26
|  |  | STW 3.2.8 | UEC DG approval of System UEC Improvement Plan 25/26 | Ian Bett | 2025-01-28 | 2025-01-28
|  |  | STW 3.2.9 | Revise the PMO framework for Improvement Plan 25/26, consistent with redesigned System PMO (Task ID 4.4.4). | Gareth Wright | 2025-02-01 | 2025-02-24
|  |  | STW 3.2.10 | PMO PIDs, Benefits, Actions for Improvement Plan 25/26 to be approved by UEC DG 25 Feb 25 meeting. | Gareth Wright | 2025-02-25 | 2025-02-25
|  |  | STW 3.2.11 | PMO PIDs, Benefits, Actions for Improvement Plan 25/26 to be approved by System Transformation Group 26 Mar 25 meeting. | Ian Bett | 2025-03-01 | 2025-03-26
|  |  | STW 3.2.12 | Governance and oversight of the delivery of the plan by UEC delivery group. | Ian Bett | 2025-04-01 | 2026-03-31

## STW UEC Risks Mitigations
[8 empty] | Initial Rating |  |  |  |  | Target risk score
SIIP Risk ID | Strategic Pledge/ Purpose | Date opened | Risk title and description | Opportunity | Existing key controls | Existing source of assurance | Gaps in controls / assurances | C | L | Score | Risk Score Trend | Mitigating Actions | C2 | L2 | Score2 | Director or risk owner | Risk Owner | Committee/Board Oversight | Amendments name and date
STWUEC 1 | AtED/CC | 2024-04-19 | Inability to fund proposed changes and commissioning requirements after successful A-tED tests of change. |  |  | System improvement programme workstream, reporting to UEC Delivery Group |  | 4 | 3 | 12 |  | Clear evidence of benefits related to any investment. Non recurrent funding has been sourced Longer term commissioning intentions will ensure integrated care model defied and will align with local care & HTP | 4 | 2 | 8 | CDO |  | UEC Delivery Group
STWUEC 2 | 4 Hr | 2024-03-12 | Unable to align workforce to meet ED demand or staff capacity to drive change​ |  |  | SaTH weekly Transformation Group meetings. Monthly UEC Transformation Assurance Committee |  | 4 | 5 | 20 |  | SaTH recruited to full ED consulant establishment. Workforce review required to align workforce to demand. | 4 | 4 | 16 | COO SaTH |  | UEC Delivery Group
STWUEC 3 | Frailty | 2024-04-24 | System care records are not integrated between providers to share Rockwood score appropriately​ |  |  | System improvement programme workstream, reporting to UEC Delivery Group |  | 4 | 4 | 16 |  | Digital enabling will be required across multiple providers in the mean time a interim solution will be implemented | 4 | 3 | 12 | CMO |  | UEC Delivery Group
STWUEC 4 | Acute Med / IPS | 2024-03-12 | Availability of workforce and funding to deliver enhanced 7-day model​ |  |  | SaTH weekly Transformation Group meetings. Monthly UEC Transformation Assurance Committee |  | 4 | 5 | 20 |  | Providers reviewing how they can use existing capacity to provide better coverage across 7 days | 4 | 4 | 16 | COO SaTH |  | UEC Delivery Group
STWUEC 5 | Discharge | 2024-04-30 | System-wide Discharge workstream: Patients are at risk of deconditioning due to length of acute stay.​ |  |  | System improvement programme workstream, reporting to UEC Delivery Group |  | 4 | 4 | 16 |  | plans to reduce long ambulance handover delays, optimising short stay capacity for frail/elderly cohort and SDEC. Actions to reduce LoS + SaTH deconditioning programme | 4 | 3 | 12 | CDO |  | UEC Delivery Group
STWUEC 6 |  | 2024-10-01 | Resource constraints in programme management, BI, clinical leadership and improvement capability. |  |  | System improvement programme identifies key clinical leads and support required for delivery |  | 4 | 4 | 16 |  | Detailed resource plan identifies need. External support provided by national teams (ECIST Tier 1 GIRFT).External support in place to develop a system Programme Management Office by Nov 24. | 4 | 2 | 8 |  |  | UEC Delivery Group
STWUEC 7 |  | 2024-10-01 | Clinical workforce already stretched. However, they are key to delivering the additional aims of A-tED, IPS and Frailty models. |  |  | System improvement programme identifies key leads and support required for delivery |  | 4 | 4 | 16 |  | To be addressed through detailed implementation planning and support of national teams. | 4 | 2 | 8 |  |  | UEC Delivery Group
STWUEC 8 |  | 2024-10-01 | Commissioning & Contracting implications on some projects relating to care coordination will delay final operating model. |  |  | Improvement plan SRO (CDO) working closing with ICB Director of Commissioning & Contracting |  | 4 | 3 | 12 |  | Commissioning approach signed off by NHS STW w.c. 6th May. Commissioning plan now being implemented with stakeholder engagement in progress. | 4 | 2 | 8 |  |  | UEC Delivery Group

## STW Governance Summary
STW System Transition Criteria - Governance |  |  | CEO Lead Simon Whitehouse, Exec Lead Alison Smith, Programme Lead Beth Emberton
DETAIL: What you need to deliver against to exit the Recovery Support Programme (RSP) and transition from NOF4 to NOF3 | Metric ID | System Deliverable Owner | KEY DELIVERABLES: The outputs that you need to produce to demonstrate delivery of exit criteria | METRICS: The measure you will track to understand if the deliverables are delivering the right results | MILESTONES / TRAJECTORY: What needs to be achieved and by when to transition from NOF4 to NOF3 by March 2026 | EVIDENCE Where the metrics are currently reported (or where could we get this data from) and/or any specific deliverables required as evidence of delivery
Implement sufficient programme management and governance arrangements across system providers to enable delivery and reporting of improvement, with immediate focus being on Finance and U&EC. | 4.1 | Alison Smith | System governance structure at Level 2 of the ICB/System, Governance structure for Finance, UEC and Workforce re-designed, implemented and functioning (balancing finance, quality & safety, performance and workforce) | NA - success will be measured through delivery of the finance, workforce and UEC exit criteria Potential balancing metric re maintaining quality - System Quality Risk Register score | Review current structure at Level 2 for UEC, Finance and workforce + interface with provider governance structures - December 24. Proposals for change made to IC Board taking into account development of provider collaborative - March 25 System Quality Risk Register score improving | System governance structure and associated terms of reference documented and signed off by ICB and provider boards (where appropriate) System Transformation Group monthly reports - showing progress of delivery of improvement plans System quality risk register
| 4.2 | Julie Garside | System performance & accountability framework designed, implemented and functioning | NA - success will be measured through delivery of the finance, workforce and UEC exit criteria | NA - success will be measured through delivery of the finance, workforce and UEC exit criteria | System performance & accountability framework documented and signed off by ICB and provider boards System Transformation Group monthly reports - showing progress of delivery of improvement plans
| 4.3 | Alison Smith | An agreed provider wide risk management approach (including consistent policies and risk assessment tools) that is then adopted as the system and ICB approach that is implemented and functioning. | Mitigations of shared risks for finance, UEC and workforce are successfully reducing the number of risks and/or risk scores for these delivery programmes | Consistent risk management policies adopted by ICB and provider boards (with the exception of MPUFTgiven covergae across other ICB areas) and being used - to include risk scroing, risk reporting/escaltion, risk management procedures - April 25. System Overall Risk Register score improving | System wide risk management approach (including consistent policies and risk assessment tools) documented and signed off by ICB and provider boards (where appropriate) Risk Registers held at Tier 2 Delivery Groups System Transformtion Group - monthly reporting includes risk reporting by programe System overall risk register
| 4.4 | Ian Bett | System PMO designed, implemented and functioning | NA - success will be measured through delivery of the finance, workforce and UEC exit criteria | NA - success will be measured through delivery of the finance, workforce and UEC exit criteria | System PMO structure & approach documented and signed off by ICB and provider boards System Transformation Group monthly reports - showing progress of delivery of improvement plans

## STW Governance Plan
Metric ID | Deliverable(s) The outputs that you need to produce to demonstrate delivery of exit criteria | Deliverable Owner | Task ID | Task(s) The tasks you need to complete to produce the deliverables (please add / remove lines as necessary) | Task Owner | Start Date | End Date
4.1 | System governance structure at Level 2 of the ICB/System, Governance structure for Finance, UEC and Workforce re-designed, implemented and functioning (balancing finance, quality & safety, performance and workforce) | Alison Smith | STW 4.1.1 | Mapping of current level 2 meeting arrangements | Alison Smith | 2024-09-01 | 2024-11-08
|  |  | STW 4.1.2 | Gap analysis of current arrangements | Alison Smith | 2024-11-11 | 2024-11-29
|  |  | STW 4.1.3 | Options appraisal produced and shared for discussions | Alison Smith | 2024-12-02 | 2024-12-20
|  |  | STW 4.1.4 | Updated level 2 meeting structure mapped and shared | Alison Smith | 2025-01-06 | 2025-01-24
|  |  | STW 4.1.5 | Final Level 2 meeting structure submitted to ICB Board for approval | Alison Smith | 2025-01-27 | 2025-03-26
|  |  | STW 4.1.6 | Level 2 meeting strcuture implemented/operational | Alison Smith | 2025-04-01 | 2026-03-31
4.2 | System performance & accountability framework designed, implemented and functioning | Julie Garside | STW 4.2.1 | Seek examples of best practices / gather existing system partner frameworks | Julie Garside | 2024-10-01 | 2024-10-25
|  |  | STW 4.2.2 | Draft system framework | Julie Garside | 2024-10-31 | 2024-11-28
|  |  | STW 4.2.3 | Share draft and develop final framework with system partners | Julie Garside | 2024-11-29 | 2024-12-23
|  |  | STW 4.2.4 | Finalise framework by end of Dec/ partner and ICB sign off by end of Jan 25. | Julie Garside | 2024-12-31 | 2025-01-31
|  |  | STW 4.2.5 | Implement during Feb/March. Functioning from 1st April 25 | Julie Garside | 2024-02-01 | 2026-04-01
|  |  | STW 4.2.6 | Quarterly reviews to ensure effectiveness. | Julie Garside | 2024-04-01 | 2026-03-31
4.3 | An agreed provider wide risk management approach (including consistent policies and risk assessment tools) that is then adopted as the system and ICB approach that is implemented and functioning. | Alison Smith | STW 4.3.1 | Provider Governance Leads and ICB Chief Business Officer meet to agree scope of work and timeline | Alison Smith | 2024-10-01 | 2024-10-30
|  |  | STW 4.3.2 | Governance approval timelines identfiied and agreed | Alison Smith | 2024-10-31 | 2024-11-08
|  |  | STW 4.3.3 | Identification of risk and barriers | Alison Smith | 2024-11-11 | 2024-11-29
|  |  | STW 4.3.4 | Sharing of Current policies and table of comparison exercise to identify options for moving to one model | Alison Smith | 2024-12-02 | 2024-12-20
|  |  | STW 4.3.5 | Produce draft policy for sharing with governance leads for comment | Alison Smith | 2025-01-27 | 2025-03-26
|  |  | STW 4.3.6 | Sign off of new policy at providers and NHS STW in line with internal and system governance arrangements. | Alison Smith | 2025-03-01 | 2025-03-31
|  |  | STW 4.3.7 | Socialise policy with organisation governance committees | Alison Smith | 2025-01-27 | 2025-03-26
|  |  | STW 4.3.8 | Policy adoption across the system | Alison Smith | 2025-04-01 | 2026-03-31
|  |  | STW 4.3.9 | Post approval review of effectiveness with sample of staff working at system level | Alison Smith | 2025-06-01 | 2025-06-30
4.4 | System PMO designed, implemented and functioning | Ian Bett | STW 4.4.1 | Commence Four-week System PMO review (building on Phase 1 recommendations and prior reviews). | PWC | 2024-08-15 | 2024-09-26
|  |  | STW 4.4.2 | Review current PMO architecture and propose System PMO implementation plan. | PWC | 2024-08-15 | 2024-09-26
|  |  | STW 4.4.3 | Final report and implementation plan due. | PWC | 2024-09-26 | 2024-10-18
|  |  | STW 4.4.4 | Standardisation of templates, reporting frameworks, use of technology, and criteria for reporting status, risk, and delivery confidence. | PWC & PMO | 2024-11-18 | 2024-12-06
|  |  | STW 4.4.5 | Ongoing review on the effectiveness of the above. | PMO | 2024-12-18 | Ongoing
|  |  | STW 4.4.6 | Implemented enhanced FIP governance to support accountability and assurance. | PMO | 2024-11-18 | 2024-12-06
|  |  | STW 4.4.7 | Improve tracking and reporting of FIP delivery and pipeline development | PMO | 2024-11-18 | 2024-12-06
|  |  | STW 4.4.8 | PwC to issue a System PMO handbook detailing templates, processes, guidance, and staff roles and responsibilities | PWC | 2024-11-18 | 2024-12-06
|  |  | STW 4.4.9 | System to iteratively provide resource between 26/09 and 06/12 for incorporation and upskilling. | PMO | 2024-09-26 | 2024-12-06
|  |  | STW 4.4.10 | PwC to run multiple upskilling sessions prior to departure. | PWC | 2024-11-18 | 2024-12-06

## STW Governance Risks Mitigation
[8 empty] | Initial Rating |  |  |  |  | Target risk score
SIIP Risk ID | Strategic Pledge/ Purpose | Date opened | Risk title and description | Opportunity | Existing key controls | Existing source of assurance | Gaps in controls / assurances | C | L | Score | Risk Score Trend | Mitigating Actions | C2 | L2 | Score2 | Director or risk owner | Risk Owner | Committee/Board Oversight | Amendments name and date
STWGOV 1 |  | 2024-10-01 | The project may require significant human resources to map, re-design and implement the governance structure. There is a risk of underestimating the time and resources needed, leading to delays or reduced deliverable/project quality. |  | Recruitment to NHS STW Governance and Corporate Affairs Team |  |  | 2 | 3 | 6 |  | Resource planning: Perform a detailed resource assessment early in the project, identifying the personnel and time needed. System support: Use colleagues froms across the system to support in mapping exercise. | 2 | 2 | 4 | Alison Smith | Alison Smith | System Transformation Group
STWGOV 2 |  | 2024-10-01 | Different providers may have varying risk management cultures, priorities, and tools. Achieving consensus on a unified approach could be challenging, particularly when balancing different risk appetites and regulatory requirements. |  | Discussions across the system already taking place. SCHT and RJAH already aligned. |  |  | 3 | 3 | 9 |  | Inclusive consultation process: Engage key stakeholders early in the design phase to gather input and build consensus on the risk management approach. Customisation with flexibility: Ensure that while the core risk management principles and tools are standardised, there is room for customisation to meet specific provider needs without compromising overall consistency. Clear communication of benefits: Highlight the advantages of a unified risk management approach, such as better oversight, reduced duplication, and improved patient safety, to get buy-in from all providers. | 3 | 2 | 6 | Alison Smith | Alison Smith | System Transformation Group
STWGOV 3 |  | 2024-10-01 | Providers don’t agree, buy into and comply with the new framework , undermining it's effectiveness. |  | Discussions already taking place across the system. |  |  | 4 | 3 | 12 |  | Inclusive design process: Involve key stakeholders (e.g., clinicians, finance teams, operations leaders, etc.) in the development of the framework to ensure their perspectives are considered and incorporated. Clear communication of benefits: Communicate the value of the framework to stakeholders, such as improved performance, enhanced patient outcomes, and better alignment of system goals. Leadership endorsement: Secure strong backing from senior leadership to promote the importance of the framework and foster organisational and system commitment to its success. | 4 | 2 | 8 | Julie Garside | Julie Garside | QPC
STWGOV 4 |  | 2024-09-01 | Inadequate resource may limit the long-term viability of the PMO |  | Recruitment in place, streamlining existing resource across STW focusing on priorities. |  |  | 4 | 3 | 12 |  | PWC to support the identification of suitability qualified resource across the system,provide training, upskilling, and on-the-job learning. | 4 | 2 | 8 | Ian Bett | Ian Bett | Financial Improvement Programme Group /System Transformation Group
STWGOV 4 |  | 2024-09-01 | Complexity arising from potential PMO duplication across the system PMO teams |  | Implementation of System PMO Tool |  |  | 4 | 3 | 12 |  | PWC to support System and composite PMO's through a process of standardisation, integration, and alignment prior to departure. | 4 | 2 | 8 | Ian Bett | Ian Bett | Financial Improvement Programme Group /System Transformation Group

## STW Leadership Summary
STW System Transition Criteria - Leadership |  |  | CEO Lead Simon Whitehouse, Exec Lead Lorna Clarson, Programme Lead Beth Emberton
DETAIL: What you need to deliver against to exit the Recovery Support Programme (RSP) and transition from NOF4 to NOF3 | Metric ID | System Deliverable Owner | KEY DELIVERABLES: The outputs that you need to produce to demonstrate delivery of exit criteria | METRICS: The measure you will track to understand if the deliverables are delivering the right results | MILESTONES / TRAJECTORY: What needs to be achieved and by when to transition from NOF4 to NOF3 by March 2026 | EVIDENCE Where the metrics are currently reported (or where could we get this data from) and/or any specific deliverables required as evidence of delivery
Demonstrate collaborative decision-making at both system and organisational levels, based on the principle of delivering the best, most sustainable and most equitable solutions for the whole population served by the system | 5.1 | Patricia Davies | Functioning Provider Collaborative (aligned to the priorities within the Strategic Commissioning Plan approved by Board) where open and honest conversations are brokered. | Provider Collaborative elements of the Integrated System Improvement Plan e.g. UEC, Finance and Workforce External assessments (initial & follow-up) of the effectiveness of the Provider Collaborative Provider Collaborative delegated programmes of work plan for 2024/25 & 25/26 | Provider collaborative elements of UEC, Finance and Workforce System Integrated Improvement Plan delivering from Sept 24 External assessment [Q4 24/25] and subsequent plan to improve Follow-up assessment [Q3 25/26] demonstrating planned improvement Governance and assurance mechanism developed and implemented for the ICB delegated programmes of work by March 25. | Provider Collaborative terms of reference Agreed Provider Collaborative priorities with timelines Provider Collaborative risk register Impact of Provider Collaborative on UEC, workforce & finance Feedback from first external assessment Plan to address findings Feedback from follow up assessment showing improvement from first Board papers evidencing collaborative decision making (sustainability) Governance and assurance mechanism – ICB to evidence.
| 5.2 | Claire Parker | Development and implementation of two Place committees to enable increased autonomy and delegation of local decision-making. | Stakeholder feedback on the effectiveness of the place committees. Improvements in health outcomes at practice/ward level population profiles. Place delegated duties and resources commissioning plan for 2024/25. Place delegated duties and resources commissioning plan for 2025/26. | Both committee terms of reference developed by end of September 2024 and formally approved by the end of November 24. Conduct Stakeholder survey by July 2025 Place Commissioning plans for 2024/25 by end of October 24 and 25/26 -by end of March 25. Delegated duties and resources from the ICB dependent on national delegation. | Committee terms of reference – ICB to evidence. Population health outcome data summarised in Integrated Care Strategy– ICB to evidence. Stakeholder survey feedback
| 5.3 | Julie Davies | Demonstrate collaborative decision-making through the co-development and co-delivery of an Integrated System Improvement Plan that supports delivery of all the RSP exit criteria at both system and organisational levels, based on the principle of delivering the best, most sustainable and most equitable solutions for the whole population served by the system. | System Integrated Improvement Plan External assessments (initial & follow-up) of collaborative decision making | System Integrated Improvement Plan by [end Oct 24] External assessment [Q4 24/25] and subsequent plan to improve Follow-up assessment [Q3 25/26] demonstrating planned improvement | System Integrated Improvement Plan signed off by ICB and provider boards and NHS England Agreed evidence for all RSP exit criteria Evidence from committees and delivery groups - agendas and minutes of decisions taken Feedback from first external assessment Plan to address findings Feedback from follow up assessment showing improvement from first
| 5.4 | Alex Brett | Clear culture and leadership improvement programme and evidence of a positive shift in staff experience through pulse survey/NHS staff survey. | Pulse Survey results (baseline 23/24) NHS staff survey (baseline 23/24) CEO Organisational Development Programme Exec development programme | Improved pulse & NHS staff survey results in 24/25 and response rate in 25/26 CEO and System Exec Organisational Development Programme agreed by end of Jan25 and delivered by March 26 | Improved pulse & NHS staff survey results 24/25 & response rate for 25/26 Delivery of a CEO Organisational Development Programme Delivery of Exec development programme

## STW Leadership Plan
Metric ID | Deliverable(s) The outputs that you need to produce to demonstrate delivery of exit criteria | Deliverable Owner | Task ID | Task(s) The tasks you need to complete to produce the deliverables (please add / remove lines as necessary) | Task Owner | Start Date | End Date
5.1 | Functioning Provider Collaborative (aligned to the priorities within the Strategic Commissioning Plan approved by Board) where open and honest conversations are brokered. | Patricia Davies (Nigel Lee) | 5.1.1 | Co-produce and agree a Provider Alliance approach | Patricia Davies | 2024-07-01 | 2025-04-01
|  |  | 5.1.2 | Determine Leadership of Provider Alliance (including lead CEO and Executive supporting infrastructure) | Patricia Davies | 2024-04-01 | 2025-04-01
|  |  | 5.1.3 | Identification of key priority workstreams with associated deliverables, accountabilities and impact | Patricia Davies | 2024-10-01 | 2025-04-01
|  |  | 5.1.4 | Develop Governance model, reporting arrangements and aligned risk management approach | Patricia Davies | 2024-10-01 | 2025-04-01
|  |  | 5.1.5 | Prepare for the findings of any external assessments and monitor the progress of any associated action plans | Patricia Davies | 2024-10-01 | 2025-04-01
5.2 | Development and implementation of two Place committees to enable increased autonomy and delegation of local decision-making. | Claire Parker | 5.2.1 | TWIPP and ShIPP committees now formal subcommittees of the ICB | Claire Parker | 2024-04-15 | 2024-07-31
|  |  | 5.2.2 | Place based strategies agreed by TWIPP & SHIP | Claire Parker | 2024-07-01 | 2024-09-30
|  |  | 5.2.3 | Delegated duties and resources | Claire Parker | 2024-09-02 | 2026-03-31
|  |  | 5.2.4 | Stakeholder feedback on effectiveness of Place committees | Claire Parker | 2025-01-07 | 2025-07-31
|  |  | 5.2.5 | Place based metrics and dash boards-in progress | Claire Parker | 2024-07-01 | 2024-12-31
5.3 | Demonstrate collaborative decision-making through the co-development and co-delivery of a System Integrated Improvement Plan that supports delivery of all the RSP exit criteria at both system and organisational levels, based on the principle of delivering the best, most sustainable and most equitable solutions for the whole population served by the system. | Julie Davies | 5.3.1 | Hold Engagement Sessions on each Transition Criteria draft deliverables, metrics, milestones and evidence | Julie Garside | 2024-08-01 | 2024-08-22
|  |  | 5.3.2 | Hold Workshops with each provider and system on deliverable high-level action plans | Julie Garside | 2024-10-03 | 2024-10-03
|  |  | 5.3.3 | Final Draft System Integrated Improvement Plan Circulated for final review and comment | Julie Garside | 2024-10-23 | 2024-11-01
|  |  | 5.3.4 | Final System Integrated Improvement Plan Approved at Providers Boards and ICB | Julie Garside | 2024-11-04 | 2024-11-27
|  |  | 5.3.5 | Performance Management of System Integrated Improvement Plan | Julie Garside | 2024-12-01 | 2026-03-31
|  |  | 5.3.6 | External assessment of collaborative decision making demonstrated in delivery of the SIIP | Julie Garside | 2025-02-04 | 2025-02-28
|  |  | 5.3.7 | Incorporate feedback into the refreshed plan for 25/26 | Julie Garside | 2025-03-03 | 2025-03-14
|  |  | 5.3.8 | Follow up external assessment of collaborative decision making demonstrated in delivery of the SIIP | Julie Garside | 2025-10-01 | 2025-10-15
5.4 | Clear culture and leadership improvement programme and evidence of a positive shift in staff experience through pulse survey/NHS staff survey. | Alex Brett (Beth Emberton) | 5.4.1 | Seek Funding Confirmation from NHSE | Bethan Emberton | 2024-06-01 | 2024-10-31
|  |  | 5.4.2 | Identify a Provider(s) to deliver CEO and Execs OD Programme | Bethan Emberton | 2024-08-01 | 2024-10-31
|  |  | 5.4.3 | Work with the Provider to develop a CEO and Execs OD Programme | Bethan Emberton | 2024-10-01 | 2024-10-31
|  |  | 5.4.4 | Provider to hold 1:1 sessions with each CEO in advance of 1st OD session with CEOs | Alex Brett | 2024-10-31 | 2024-11-26
|  |  | 5.4.5 | First scoping session with system CEOs | Alex Brett | 2024-11-27 | 2024-11-27
|  |  | 5.4.6 | Detailed CEO and system Execs OD programme developed | Alex Brett | 2024-11-27 | 2024-12-20
|  |  | 5.4.7 | Detailed CEO and system Execs OD programme approved at STG | Alex Brett | 2025-01-29 | 2025-01-29
|  |  | 5.4.8 | Detailed CEO and system Execs OD programme implemented | Alex Brett | 2025-01-29 | 2026-03-31
|  |  | 5.4.9 | Analysis of 2024 NHS staff survey results | Alex Brett | 2025-02-01 | 2025-03-31
|  |  | 5.4.10 | Ongoing monitoring of pulse survey and NHS satff survey metrics. | Alex Brett | 2025-02-01 | 2026-03-31

## STW Leadership Risks Mitigation
[8 empty] | Initial Rating |  |  |  |  | Target risk score
SIIP Risk ID | Strategic Pledge/ Purpose | Date opened | Risk title and description | Opportunity | Existing key controls | Existing source of assurance | Gaps in controls / assurances | C | L | Score | Risk Score Trend | Mitigating Actions | C2 | L2 | Score2 | Director or risk owner | Risk Owner | Committee/Board Oversight | Amendments name and date
STWLEAD 1 |  | 2024-10-23 | Risk to ability to delegate if national guidance is delayed |  | Finance partners have links to place based committes and SHIP/TWIP reviewing in meetings any potentially identfiable delegations | TWIP/SHIP |  | 3 | 3 | 9 |  | Reviewed ToR for SHIP and TWIP, delegation and finance input minuted at place committees. Agreement to review each commitee for any gaps or issues | 3 | 2 | 6 | Claire Parker | Claire Parker | Integrated Care Board
STWLEAD 2 |  | 2024-10-01 | Developing an effective governance structure for the provider collaborative can be challenging. Each Trust has different governance models, and integrating these into a single decision-making framework could lead to delays or inefficiencies. |  | NHS Trust governance colleagues and legal services already engaged. |  |  | 4 | 4 | 16 |  | Collaborative governance model: Design of a governance structure that ensures equitable representation from all four NHS Trusts. Clear roles and responsibilities: Establish clear roles, responsibilities, and decision-making processes within the collaborative governance structure to avoid confusion and duplication of efforts. Escalation pathways: Develop clear escalation procedures for resolving governance-related conflicts, ensuring that issues are addressed promptly and fairly. | 4 | 2 | 8 | Patricia Davies | Patricia Davies | Integrated Care Board
STWLEAD 3 |  | 2024-10-01 | There is a risk that the plan will not go through all appropriate governance routes before 27th November 2024. |  | Scoping exercise taking place to map out appropriate governance routes within organisations. |  |  | 3 | 3 | 9 |  | Scoping exercise taking place to map out appropriate governance routes within organisations | 3 | 2 | 6 | Julie Garside | Julie Garside | System Transformation Group
STWLEAD 4 |  | 2024-10-01 | There is a risk around the capacity of the MPUFT OD team to deliver the OD programme. |  | Scoping exercise taking place with MPUFT as to how funding can be used to support with capacity and delivery of the programme. |  |  | 4 | 3 | 12 |  | Scoping exercise taking place with MPUFT as to how funding can be used to support with capacity and delivery of the programme. | 3 | 3 | 9 | Alex Brett | Alex Brett | System Transformation Group
STWLEAD 5 |  | 2024-10-01 | Risk to collaborative system decision-making if there is no unified direction, to align on goals, improve productivity, and drive cohesive strategies. |  | Monthly STG meeting in place. Monthly CEOS meeting in place. |  |  | 4 | 3 | 12 |  | System organisational development programme developed and being implemented, funded from RSP. The OD programme aims not only to build trusting partner relationships to support collaborative decision-making, but also develop a unified system direction and alignment of goals which will improve productivity and drive cohesion of our organisational and system strategies. | 3 | 3 | 9 | Lorna Clarson | Lorna Clarson | System Transformation Group
STWLEAD 6 |  | 2024-10-01 | Changes in senior leadership across the ICB and SATH may risk pace of programme delivery while individuals embed into roles. |  | Monthly STG meeting in place. Monthly CEOS meeting in place. |  |  | 4 | 3 | 12 |  | Regular system CEO networking embedded in system governance structure to support the development of positive and constructive relationships. Supportive handover processes in place for all leaders using existing governance and improvement plans to maximise delivery and opportunity. | 3 | 3 | 9 | Lorna Clarson | Lorna Clarson | System Transformation Group